## Migration-Tracker
S.No | Tool Name | Current Account | New Service Account | Usage / Purpose | Location / Configuration Area | Action Required | Owner | Status | Comments
1 | Bitbucket | Yes | svc-bb-cbcd | PR creation & master merge | Branch permissions | Replace SCT with svc-bb-cbcd | SCM
2 | Bitbucket | Yes | svc-bb-cbcd | Write+merge permissions | Project → Branch Permissions | Update branch rules | SCM
3 | Bitbucket | Yes | svc-bb-hooks | Hooks trigger CI | Hooks settings | Update hook credentials | SCM
4 | Bitbucket | Yes | svc-bb-cbcd | PR approval | Repo settings | Assign roles | SCM
5 | Bitbucket (Global) | Yes | None | Global admin removal | Global permissions | Remove SCT admin access | SCM
6 | CloudBees CI | Yes | svc-cbci-bb | Git checkout | CJOC credentials | Add new credential | CI Team
7 | CloudBees CI | Yes | svc-cbci-bb | Multibranch SCM | Job config | Update credential ID | CI Team
8 | CloudBees CI | Yes | svc-cbci-bb | Shared libraries | Global Pipeline Libraries | Replace SCT | CI Team
9 | CloudBees CI (Sonar) | Yes | svc-cbci-sonar | Sonar scan auth | CJOC credentials | Create sonar token + update | CI Team
10 | SonarQube | Yes | svc-cbci-sonar | Token authentication | User Tokens | Create token & assign role | Sonar Admin
11 | CloudBees CD | Yes | svc-bb-cbcd | PR creation | Component process | Update API credentials | CD Team
12 | CloudBees CD | Yes | svc-bb-cbcd | Master merge | Release process | Replace SCT | CD Team
13 | CloudBees CD | Yes | svc-bb-cbcd | REST API calls | Shell tasks | Update credentials | CD Team
14 | Hooks | Yes | svc-bb-hooks | CI job trigger | Hook config | Replace credentials | SCM
15 | Audit | Yes | — | Tool inventory | All tools | Verify no SCT usage | DevOps Lead
16 | Cleanup | Yes | — | Decommission SCT | All tools | Disable after validation | DevOps Lead

## Validation-Plan
Test Case | Tool | Expected Result | Performed By | Status | Notes
Git checkout using svc-cbci-bb | CBCI | Checkout succeeds | CI Team
PR creation | CBCD | PR created via svc-bb-cbcd | CD Team
Master merge | CBCD | Merge succeeds | CD Team
Hook trigger | Bitbucket | CBCI job triggered | SCM
Sonar scan with new token | CBCI | Scan authenticates | CI Team
Branch permission validation | Bitbucket | Only svc-bb-cbcd can merge | SCM
Remove SCT | All | No failures | DevOps

## Cutover-Plan
Step No | Task | Owner | Status | Comments
1 | Create new service accounts | IAM Team
2 | Generate Sonar tokens for new SA | Sonar Admin
3 | Add new SAs to Bitbucket | SCM Team
4 | Update CBCI Bitbucket credentials | CI Team
5 | Update CBCI Sonar credentials | CI Team
6 | Update CBCD Bitbucket credentials | CD Team
7 | Update Hooks | SCM Team
8 | Full validation | DevOps
9 | Remove SCT account from tools | DevOps/SCM
10 | Disable SCT account | IAM Team